# Review of HE student outcomes and destinations data

# Working group meeting

**11.00 – 15.00 Thursday 19 November 2015**

**etc.venues Liverpool Street, Bishopsgate Court, 4-12 Norton Folgate, London, E1 6DQ**

Paper No: 4

# Timescales and communications

Regular updates will be made to the HESA website at <https://www.hesa.ac.uk/content/view/3041/209/> to reflect the work of the Review.

Consultations will be arranged to maximise engagement with stakeholders.

The outline plan of work is as follows:

|  |  |
| --- | --- |
| **Activity** | **Timescale** |
| Launch review | 20 July 2015 |
| First Strategic Group meeting (agree remit) | 16 November 2015 |
| First Working Group meeting (develop work programme) | 19 November 2015 |
| Second Working Group meeting (plan consultations) | December 2015 |
| Consultation on requirements (multi-strand) | January & February 2016 |
| Third Working Group meeting (develop outline specification and business case) | February & March 2016 |
| Consultation on proposals | April & May 2016 |
| Fourth Working Group meeting (finalise specification and business case) | May 2016 |
| Second Strategic Group meeting (review and endorse business case) | June 2016 |
| Summary of changes specified and implementation plan produced | Summer 2016 |

The above schedule of activities and timescales will be used to inform the development of the detailed work plan and an associated communications plan.

The Business case will specify the implementation path and onward timescales for collection development work, data collection and publication.

DC

2015-10-30