**Review of HE student destinations and outcomes data:**

**Third working group meeting**

## Monday 22 February 2016, 11.00am

**Finlaison House, London, EC4A 1AB**

Paper No: 1

# Work plan

This paper lays out a proposed revised plan of work for the review. Given the revised timescales for the Green Paper/TEF in England, and the less-clear responses to the SBEE Act in the other administrations of the UK, we believe that it is in order to revise the timescales for the review, and push-back some activities.

Working group activity

Strategic group activity

Events

Consultation information

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | February | March | April | May | June | July |
| HEPISG meeting | 18 February |  |  |  |  |  |
| UUK Student Policy Network | 19 February |  |  |  |  |  |
| Working group meeting 3 | 22 February |  |  |  |  |  |
| HESA draft consultation | 23 – 26 February |  |  |  |  |  |
| Working group comment on consultation | 26 February – 4 March | |  |  |  |  |
| Strategic group comments on consultation |  | 4 – 11 March |  |  |  |  |
| Consultation on requirements and principles |  | 15 March – 31 May | | |  |  |
| Westminster Higher Education forum |  |  | 12 April |  |  |  |
| Working group meeting 4 |  |  | Propose combining with ‘conference’ |  |  |  |
| HESA blog post published |  |  | 25 – 29 April |  |  |  |
| Publish outputs from research projects |  |  |  | 1 - 5 May |  |  |
| HESA destinations conference |  |  |  | 5 – 13 May |  |  |
| Develop proposals for consultation |  |  |  | 9 May – 30 June | |  |
| Working group meeting 5 |  |  |  |  | 13 June – 24 June |  |
| Strategic group meeting 2 |  |  |  |  | 17 – 30 June |  |
| Consultation on detailed proposals |  |  |  |  | 27 June – 1 September | |
| Meeting of Strategic and Working groups to finalise. |  |  |  |  | Autumn 2016 | |
| Autumn 2016 | |
| Business case and implementation plan published |  |  |  |  | Autumn 2016 | |

Rachel Hewitt & Dan Cook

12/02/2016